## Sheet1
Project: | My First MVC Web Application
Sprint # | 1
| ID | User Story | Tasks | Assigned To | Status | Estimated (Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10
| 1 | I need to change the default website to my own. | Create a MVC. | Renier | Completed | 0.3 | Day 1: 0.25
|  |  | Change Views. | Renier | Completed | 0.3 | Day 1: 0.25
|  |  | Create a Viewbag and add it to my website. | Renier | Completed | 0.3 | Day 1: 0.3
| 2 | Save my first project as completed. | Create a Folder for my Portfolio. | Renier | Completed | 0.3 | Day 1: 0.25
|  |  | Complete my Project. | Renier | Completed | 0.3 | Day 1: 0.45
3
| Ideal - Remaining effort in uninterrupted working hours |  |  |  |  | 1.5 | 1.35 | 1.2 | 1.05 | 0.9 | 0.75 | 0.6 | 0.45 | 0.3 | 0.15 | 0
| Actual - Remaining effort in uninterrupted working hours |  |  |  |  | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0